## Slide 1: MSC DISSERTATION Grace - Weekly Presentations

## Slide 2: Progress presentations
WEEK 1 3-6
WEEK 2 7-10
WEEK 3 11-14
WEEK 5 15 - 18
WEEK 6 19 - 22

## Slide 3: WEEK 1 & 2 What has been done - Exploratory data analysis to understand CSA data better. - Meeting with Sofiat to further understand CSA’s objectives and goals – Documented - Deep dive research on different technical methodologies that can be used for the project. - Project set up.

## Slide 4: Questions
Focus on research –review of research done vs focus on data I have

## Slide 5: Next week plan
Conduct and write up on research insight.
Problem analysis write up.
Data clean up and encoding.

## Slide 6: Overall schedule
On track
Problem analysis

## Slide 7: Week 3 & 4 - What has been done:
- Introduction, Background of methods, related work research
Cleaned and encoded features
Composite score modelling
Predictive modelling + feature importance – CS model, associations
Research & reading on Bayesian and causal inference

## Slide 8: Q&A
Unobserved data – priors?
How to assign prior distributions to such variables

## Slide 9: Next week plan
Causal Inference Modelling - code
Start on design chapter writeup

## Slide 10: Overall Schedule
On track – Design and Implementation stage
2 weeks – Causal Inference
2 weeks - Bayesian
2 weeks – Evaluations & Conclusions

## Slide 11: Week 5
- Defined and implemented a Bayesian linear regression model in PyMC- For this I started with a base model focusing on the variables that made up the composite skill score.
- Tested different sample sizes , draws and steps to ensured there were no divergences in sampling (indicating stable inference)
Did more reading on Bayesian on the implementation end and now I feel I have a solid understanding of it implementation-wise
-Code cleanup & dependencies management

## Slide 12: Q&A
The model’s SD 9 sigma is collapsing to zero , making it not converge and suggesting overconfidence. What would you suggest?
Tried Normal & Student T distributions
After trying to improving convergence, what would be the best way to validate the model

## Slide 13: Next week plan
Extend the Bayesian Modelling for the other features.
Fine tuning for base model
Start on design chapter writeup